## Sheet1
Ticketing System | Application Maintainer | Change Environment | Start Date | Urgency | Change Manager | CMS System Maintainer | Implementation Contact | System Outage? | Shared Service
Jira |  | Prod | 06/20/2026 09:00 PM EST | Normal | Michael Harkema |  | Masood Rahimi | Yes | Yes
Change Identifier | Requestor and Firm (VDC) Phone and Email | SDLC Tested Environments | End Date | Urgency Justification | Government Task Lead | Business Owner | IUSG Approver | Core Hour Outage? 6 am - 9 pm | Risk Level
|  |  | 06/21/2026 01:00 AM EST |  | Katherine Brewer |  |  | No | Low
Detailed Description of Change |  |  |  |  | All Downstream Systems Impacted by this Change
The below describes the work Cloud DevOps will be performing: Jfrog: Update EKS Nodes AMIs. Update EKS add-ons and supporting components Update application version to the latest Update Jfrog configuration to use AWSSDKv2 for artifacts fetch from S3 with correct encryption metadata Karpenter: Deploy Cost-opitmized agent nodes-pools for CBJ and Jfrog CB Jenkins : Update EKS Nodes AMIs. Update EKS add-ons and supporting components Upgrade CB Jenkins CI APP version for OC & Manage controllers to 2.555.1.36488 NO major changes. SonarQube: Upgrade the Node AMI to the latest AMI release from SecOps |  |  |  |  | ADOs on CMS Cloud AWS Commercial and GovCloud using affected DevOps JFrog Service
Communication Plans and Dates |  | Implementation Plan, Time and Duration |  | Testing Plan, Time and Duration |  | Verification Plan, Time and Duration |  | Rollback Plan, Time and Duration
CMS Cloud Weekly Change Newsletter 6/11/2026 |  | 1. Maintenance for production environment of Cloudbees - Abdul Qavi Shaik - 30 minutes - 09:00 pm EST 2. Maintenance for production environment of Cloudbees Cluster - Masood Rahimi- 30 minutes - 09:30 pm EST 3. Maintenance for production environment of Jfrog - Masood Rahimi - 30 minutes - 10:00 pm EST 4. Deployment for production environment of Karpenter - Masood Rahimi - 60 minutes - 11:00 pm EST |  | 1. Run manual tests on Jfrog, Artifactory, and Xray - Masood Rahimi - 15 minutes - 11:00 pm EST 2. Run tests on Cloudbees Cluster - Masood Rahimi - 15 minutes - 11:15 pm EST 3. Run manual tests on CloudBees CI - Abdul Shaik - 15 minutes - 11:30 pm EST 4. Run tests on Karpenter Masood Rahimi - 15 minutes 11:45 |  | 1. Verification of integration across DevOps services -Masood Rahimi - 15 minutes - 11:55 pm EST |  | 1. Rollback to previous app versions and images - 55 minutes - 12:50 am EST
: