## Instructions
Instructions for using the Project Schedule template
An Artifact Implementation plan is created to outline and define the work to be done and define the timeline for the implementation. This document includes the tasks required to manage a deployment from start to completion. It gives XOC staff information about the start and end time of major milestone. The document is used only to schedule deployment artifacts.
This template does not represent all of the work necessary to produce a product or service. Detailed tasks necessary to produce deliverables for any specific project should to be added in sections (phases) of the artifact deployment steps.
Guidelines to complete the form:
Enter information in the respective fields. If a field is not relevant to your artifact, enter "N/A".
Ensure that you mark it clearly if the artifact is an Urgent fix.
Enter background of an artifact, why it is required and what impact it would have on overall Marketplace.
Enter all points of contact involved in this deployment, including subcontractors, GTL, CMS approving authority, and points of escalation.
Delete any tasks in the template that do not pertain to your project. DO NOT delete any of the Phases.
Enter the estimated durations of each task and the targeted start date/time.
When the team has been defined, enter the person(s) responsible for each task.
Actual start and end time for an artifact will be managed by XOC, please do not enter any information in this area.
In comments / dependency section, clearly identify the dependency if any or enter your comments for a specific step.
* If you have additional steps which you feel that should be captured, add them on a separate tab.
** Please keep a separate tab for each environment that this change needs to be deployed to. Feel free to copy the existing tab and modify what is necessary for each environment.
Maintaining the Schedule (For XOC Only):
Enter actual hours, remaining hours, status and status date. Estimated hours should not change.
Questions about this form? Contact XOC BA team: hkhan@qssinc.com, jlocks_con@qssinc.com, and iolshansky@qssinc.com.

## Artifact Implementation Plan
Change Request (CR) Details
CR Title |  | CMS Cloud DevOps Service Monthly Maintenance |  |  |  | JIRA Ticket # | ITC-6160
CR # |  | MGGD-62548 |  |  |  | CALT Date
CR Date | [5 empty] | Type of Change | Data Updates & Cleanups
Go/No-Go Review Date |  | 2026-06-11 |  |  |  | Requested By | Patrick Hendren
Other CR relations (CALT, JIRA, ALM, Remedy etc): |  | N/A |  |  |  | Outage Required | YES
Successful IMP testing Date | [5 empty] | Deployment Type
Start Date & Time |  | 06/20/2026 09:00 AM EST |  |  |  | End Date & Time | 06/21/2026 01:00 AM EST
Priority |  | Low |  |  |  | Risk | Low
Overview
Description |  | Jfrog: Update EKS Nodes AMIs. Update EKS add-ons and supporting components Update application version to the latest Update Jfrog configuration to use AWSSDKv2 for artifacts fetch from S3 with correct encryption metadata Karpenter: Deploy Cost-opitmized agent nodes-pools for CBJ and Jfrog CB Jenkins : Update EKS Nodes AMIs. Update EKS add-ons and supporting components Upgrade CB Jenkins CI APP version for OC & Manage controllers to 2.555.1.36488 NO major changes. SonarQube: Upgrade the Node AMI to the latest AMI release from SecOps Systems impacted: aws-cms-oit-iusg-devops-services-prod (623510781344) aws-cms-oit-iusg-draas-awswest32 (478919403635) aws-cms-oit-iusg-gc-cbj-prod (020847197482)
Justification |  | System Security and Maintenance. Making platforms available to the Management Network Updating configuration with team needs
Impact Analysis
Systems Impacted |  | aws-cms-oit-iusg-devops-services-prod (623510781344) aws-cms-oit-iusg-draas-awswest32 (478919403635) aws-cms-oit-iusg-gc-cbj-prod (020847197482)
Infrastructure Impacted
Notes
Deployment Plan
Table 1. Points of contacts (POC) and Escalation List
Resource Management
List all teams/organization involved in implementation of the change in the table below. The list must include all parties (including at-least 2 level of escalation) involved with the implementation, as well as the government task lead (GTL) and CMS contacts.
Role |  | Name |  | Organization |  | Phone | Email |  | Alternate POC
| Escalation (Level 1) | Swamy Raj |  | Samtek |  |  |  | swamy.raj@samtek.io
Management Escalation |  | Faraaz Khan |  | Samtek |  |  | faraaz@samtek.io
Release Manager |  | Patrick Hendren |  | Samtek |  |  | patrickhendren@samtek.io
System Impacted POC |  | Max Rahimi |  | Samtek |  |  | max@samtek.io
System Impacted POC |  | Shantanu Mangalvedhekar |  | Samtek |  |  | shantanu@samtek.io
System Impacted POC |  | Abdul Shaik |  | Samtek |  |  | abdulqavi@samtek.io
System Impacted POC |  | Dev Pathak |  | Samtek |  |  | dev@samtek.io
System Impacted POC |  | Ramesh Mahimalur |  | Samtek |  |  | ramesh.mahimalur@samtek.io
Table 2. Deployment Schedule
Activity Management
Task # | Activity/Task |  | Owner |  | Est. Duration | Anticipated Start Time | Anticipated End Time |  | Current Status | Comments / Dependency
Pre-Implementation Activities
1 | Send Comms out to the application teams via GovDelivery |  | Max Rahimi
Insert additional tasks above this row
Implementation
1 | Maintenance for production environment of Cloudbees 1. Install and configure Kubectl 2. Deploy latest Chart Version of Cloudbees Core 3. Validate CJOC is running at the app Version. 4. Clean Docker image workflow. |  | Abdul Shaik |  | 30 minutes | 09:00 p.m. ET
2 | Maintenance for production environment of Sonarqube 1. Backup Database 2. Upgrade Postgres to v16 3. Update parameter store 4. Point listeners to the newly implemented instance 5. Setup sonarqube |  | Shantanu Mangalvedhekar |  | 30 minutes | 09:30 p.m. ET
3 | Maintenance for production environment of Jfrog 1. Terraform Deployment Window 2. Kubernetes Deployment Window 3. Update kubeconfig to jfrog-prod |  | Max Rahimi |  | 30 minutes | 10:00 p.m. ET
| Maintenance for production environment of Karpenter 1. Terraform Deployment Window 2. Kubernetes Deployment Window 3. Update kubeconfig to Karpenter |  | Max Rahimi |  | 30 minutes | 10:30 p.m. ET
Insert additional tasks above this row
Validation/Testing
2 | Run manual tests on Jfrog 1. Checkout to monthly maintenance branch of CMS-Enterprise/cmscloud-devops repo Get CloudTamer creds for DSO Shared Services Prod: gss-operations-admin > Short Term Access keys Paste the keys into the terminal you will be using for deployment Watch the pods rotate and keep watch for any pods that hit an Error state of any kind, or restart repeatedly. Once all of the pods have rotated, further deployments or testing can be completed. |  | Max Rahimi |  | 15 minutes | 11:00 p.m. ET
3 | Run tests on Sonarqube 1. Once https://sonarqube.cloud.cms.gov/ shows Sonarqube application, go to https://sonarqube.cloud.cms.gov/setup for Sonarqube to do database schema changes. Keep quality profiles traditional (and not Multi-Quality Rule Mode) Watch and confirm background tasks rebuilding ElasticSearch |  | Shantanu Mangalvedhekar |  | 15 minutes | 11:15 p.m. ET
4 | Run manual Tests on Cloudbees 1. Login to CJOC url and find Container Images 2. Click Delete to Outdated Version |  | Abdul Shaik |  | 15 minutes | 11:30 p.m. ET
6 | Run manual Tests on Karpenter 1. Log in to Karepenter and find Container Images 2. Click Delete to Outdated Version |  | Max Rahimi |  | 30 minutes | 12:00 p.m. ET
Insert additional tasks above this row
Rollback Plan
1 | Rollback to previous app version and image |  | Max Rahimi & Abdul Shaik |  | 55 minutes | 12:50 a.m. ET
Note on M38: Imported Author: ====== ID#AAAAQv2Kx2w Status (2021-02-24 03:45:08) Active In Process Complete